## Sheet1
Projects and Tasks BASE PLAN TASKS 1-6 | Schedule | Budget | Measureable Deliverable
Task 1. Develop Seismic Policies |  | 39126.83
1.1 Develop and Encourage Adoption of Policy Recommendations | August 2017 - Spring 2018 | 10728.91 | Hold two committee meetings of each of the three WSSPC Committees to develop approximately 5 policy recommendations on earthquake loss reduction issues. Conduct a survey of adopted policy recommendations by WSSPC members.
1.2 Conduct Board Meetings | December 2017 & Spring 2018 | 28397.92 | Hold two Board meetings; prepare agendas, reports, financial status reports, and meeting minutes.
Task 2. Provide Forums |  | 39337.48
2.1 2018 WSSPC Annual Meeting (including Awards in Excellence, Leadership and Lifetime Achievement awards) | September 2017 - Spring 2018 | 22804.05 | Meetings Notebook containing draft policy recommendations for member adoption, committee annual progress reports and minutes, and current WSSPC and cooperative agreement financial status reports, distributed electronically and posted on the WSSPC website.
Organize Awards program for 2018 that recognizes exemplary products and projects of the earthquake community: announce nominations, post deadlines for submission, hold Board conference call to determine winners, notify winners, order plaques, support modest travel to Awards ceremony, hold Awards banquet at the WSSPC annual meeting. Details of the winning programs will be distributed through press releases, meeting materials, and the WSSPC website.
2.2 Earthquake Program Managers Meeting | Fall 2017-Spring 2018 | 16533.43 | A meeting planned in collaboration with FEMA, other earthquake consortia and partners for training and earthquake education.
Task 3. Provide Outreach and Education |  | 57396.21
3.1 Website | August 2017 - July 2018 | 16404.43 | Provide an up-to-date, optimized, informative public website to educate the public and inform the earthquake community. Analyze the website usage and provide a report in the Annual Report.
3.2 Quarterly Electronic Newsletter and Monthly Bulletins | August 2017 - July 2018 | 33459.08 | Publish 4 electronic newsletters in October 2017, and January, April, and July 2018 that are distributed to subscribers and posted on the WSSPC website. Publish 8 Monthly Bulletins in the intervening months.
3.3 2017 Annual Report | Spring 2018 | 4397.7 | An Annual Report that details the activities of WSSPC uploaded to the WSSPC website for general distribution to the public, and 10 printed copies for FEMA and the WSSPC Board.
3.4 Community Education and Outreach | August 2017-October 2017 & TBD | 3135 | Conduct outreach to the local community, including fairs, teachers' conferences, ShakeOut, and other opportunities as they arise.
Task 4. Maintain and Encourage Partnerships |  | 8888.09
4.1 Maintain and Encourage Partnerships | August 2017- July 2018 | 4017.25 | Participate in joint activities (such as co-sponsoring events and trainings), to broadly disseminate and share information about earthquake risk reduction issues and policy development, attend meetings.
4.2 Affiliate Member Program | October 2017 - January 2018 | 4870.84 | Participation of Affiliates through their financial support and in a broader acceptance of policy recommendations at local levels.
Task 5. Manage Finances and Grants |  | 72751.39
5.1 Manage Cooperative Agreement | August 2017- July 2018 | 13120.84 | Monthly accounting of cooperative agreement expenses and timely submission of quarterly financial, quarterly performance reports with the Outcomes section, and reimbursement requests. Produce a final performance report and final financial report.
5.2 Manage WSSPC Finances | August 2017 - July 2018 | 20041.7 | Annual financial statements published in the Annual Report, an annual Board review of the financial policies and procedures, tax returns submitted to Dun and Bradstreet, financial reports provided to the Board of Directors, and monthly financial accounting.
5.3 Maintain Office and Support Personnel | August 2017 - July 2018 | 39588.85 | Maintenance of the office and staff, including human resources, benefits, payroll, and computer network.
Task 6. Outcomes Report |  | 7500
6.1 Prepare quarterly Outcomes Reports | October 30, 2017, January 30, 2018, April 30, 2018, July 30, 2018. | 5750 | Outcomes report section in quarterly performance report.
6.2 Prepare final Outcomes Report | July 30, 2018. | 1750 | Final Outcomes Report in the final quarter.
Task 7. Support States as Assigned by FEMA |  | 54833
7.1 Support EQ Program Managers Travel to NEPM | Spring 2018 | 19833 | Reimbursement of travel expenses for attendees to the National Earthquake Program Managers Meeting for training: New Mexico, Montana, Wyoming, Nevada, Hawaii, Guam, American Samoa, Northern Mariana Islands, Alaska, Idaho, Washington
7.2 Support Hawaii Workshop | September 2017; November 2017; February 2018; March 2018 | 35000 | Support planning, venue, and travel for workshop.
a. Secure Meeting space |  | 14000 | Meeting venue for 2 days and 100 people
b. Support travel |  | 18900 | Travel reimbursements forWSSPC, inter-island travel, and presenters
c. Support registration |  | 2100 | Name tags, registration, onsite logistics
CONTRACTS
Task 3.3 | Spring 2018 | 600 | Copy, print and laminate tabs, assemble and bind Annual Report.
Task 6.2 | September 2017 - Spring 2018 | 14000 | Contract for a workshop venue for 100 people for 2 days in Honolulu.