## Sheet1
Projects and Tasks BASE PLAN TASKS 1-6 | Schedule | Budget | Measureable Deliverable | Outcomes
Task 1. Develop Seismic Policies |  | 32698.22
1.1 Develop and Encourage Adoption of Policy Recommendations | August 2018 - Spring 2019 | 9847.46 | Hold two committee meetings of each of the three WSSPC Committees to develop approximately 5 policy recommendations on earthquake loss reduction issues. | Identify and discuss policy issues
1.2 Conduct Board Meetings | December 2018 & Spring 2019 | 22850.76 | Hold two Board meetings; prepare agendas, reports, financial status reports, and meeting minutes. | Identify and discuss policy issues, Provide oversight for policy development
Task 2. Provide Forums |  | 26418.01
2.1 2019 WSSPC Annual Meeting (including Awards in Excellence, Leadership and Lifetime Achievement awards) | September 2018 - Spring 2019 | 16900.64 | Prepare a Meetings Notebook containing draft policy recommendations for member adoption, committee annual progress reports and minutes, and current WSSPC and cooperative agreement financial status reports, distributed electronically and posted on the WSSPC website. | # attendees by state, organization
Organize Awards program for 2019 that recognizes exemplary products and projects of the earthquake community: announce nominations, post deadlines for submission, hold Board conference call to determine winners, notify winners, order plaques, support modest travel to Awards ceremony, hold Awards banquet at the WSSPC annual meeting. Details of the winning programs will be distributed through press releases, meeting materials, and the WSSPC website.
2.2 Earthquake Program Managers Meeting | Fall 2018-Spring 2019 | 9517.37 | Plan, organize, and conduct a meeting planned in collaboration with FEMA, and other earthquake consortia and partners, for training and earthquake education. | Support partners to expand reach and raise awareness
Task 3. Provide Outreach and Education |  | 68199.6
3.1 Website | August 2018 - July 2019 | 21196.29 | Provide an up-to-date, optimized, informative public website to educate the public and inform the earthquake community. Analyze the website usage and provide a report in the Annual Report. | Increased reach, Increased knowledge of earthquake hazard, risks, mitigation actions
3.2 Quarterly Newsletters and Monthly Bulletins | August 2018 - July 2019 | 36265.69 | Publish a quarterly electronic newsletter beginning in October 2018, followed by January, April, and July 2019 that is distributed to subscribers and posted on the WSSPC website. Publish 8 Monthly Bulletins in the intervening months. | Increased knowedge of earthquake hazard, risks, mitigation actions
3.3 2018 Annual Report | Spring 2019 | 6676.16 | Publish an Annual Report that details the activities of WSSPC and upload it to the WSSPC website for general distribution to the public. Provide 12 printed copies for FEMA and the WSSPC Board. | Increased reach, Increased knowledge of earthquake hazard, risks, mitigation actions
3.4 Community Education and Outreach | August 2018-October 2018 & TBD | 4061.46 | Conduct outreach to the local community, including fairs, teachers' conferences, ShakeOut, and other opportunities as they arise. | Increased reach, Increased knowledge of earthquake hazard, risks, mitigation actions
Task 4. Maintain and Encourage Partnerships |  | 7067.07
4.1 Maintain and Encourage Partnerships | August 2018- July 2019 | 3409.61 | Participate in joint activities (such as co-sponsoring events and trainings), to broadly disseminate and share information about earthquake risk reduction issues, policies, and practices; attend partner meetings. | Increased reach, # booth visitors
4.2 Affiliate Member Program | October 2018 - January 2019 | 3657.46 | Encourage participation of Affiliates through their financial support and in a broader acceptance of policy recommendations at local levels. | Increased reach, # Affiliate members
Task 5. Manage Finances and Grants |  | 89017.1
5.1 Manage Cooperative Agreement | August 2018- July 2019; October 30, 2018, January 30, 2019, April 30, 2019, July 30, 2019 | 16028.15 | Provide monthly accounting of cooperative agreement expenses and provide timely submission of quarterly financial, quarterly performance reports with the Outcomes section, and reimbursement requests. Produce a final performance report and final financial report. | Achieve milestones of FEMA grant
5.2 Manage WSSPC Finances | August 2018 - July 2019 | 27751.14 | Provide annual financial statements published in the Annual Report, an annual Board review of the financial policies and procedures, tax returns submitted to Dun and Bradstreet, financial reports provided to the Board of Directors, and monthly financial accounting. | Achieve milestones of FEMA grant
5.3 Maintain Office and Support Personnel | August 2018 - July 2019 | 45237.81 | Maintain the office and staff, including human resources, benefits, payroll, and computer network. | Achieve milestones of FEMA grant
Task 6. Outcomes Report |  | 3600
6.1 Quarterly Outcomes Report | October 2018, January 2019, April 2019, July 2019 | 2800 | Document how the outreach and education has been effective in meeting the outcomes. | Increased knowledge of earthquake hazard, risks, and mitigation actions
6.2 Final Outcomes Report | July 2019 | 800 | Document how the outreach and education has been effective in meeting the outcomes. | Increased knowledge of earthquake hazard, risks, and mitigation actions
Task 7. State Support Projects |  | 176547
7.1 Guam | August 2018 - March 2019 | 30000 | Support 2-day workshop with travel, meeting venue. | Increased knowledge of earthquake hazard, risks, and mitigation actions
7.2 Hawaii | August 2018 - June 2019 | 30000 | Support travel for 4 HETAC meetings and support outreach products. | Increased knowledge of earthquake hazard, risks, and mitigation actions
7.3 Idaho | Fall 2018 - July 2019 | 30424 | Provide exercise support products and travel reimbursements. | Increased knowledge of earthquake hazard, risks, and mitigation actions
7.4 Nevada | August -October 2018, January - April 2019 | 35123 | Conduct 2 billboard campaigns. | Increased knowledge of earthquake hazard, risks, and mitigation actions
7.5 Wyoming | August - November 2018 | 27000 | Provide specific promotional items. | Increased knowledge of earthquake hazard, risks, and mitigation actions
7.6 NEPM travel | January - June 2019 | 24000 | Reimburse travel to the National Earthquake Program Managers meeting. | Increased knowledge of earthquake hazard, risks, and mitigation actions